OG Gaming

One-Week Development Plan

Stack recommendation and SDLC schedule for the Phase 1 MVP

The plan builds Phase 1 only (the MVP from the proposal), on a managed stack (Next.js on Vercel plus Supabase) that is quick to build and needs no server administration.

# 1. Recommended Stack

| Layer | Choice | Why |
| --- | --- | --- |
| Frontend | Next.js + Tailwind + shadcn/ui | Fast to build, mobile-first, ready-made components |
| Backend | Next.js route handlers + server actions | One codebase and one deploy target; no separate API host |
| Database | Supabase Postgres | Managed; its exclusion constraint prevents double-booking at the database level |
| Migrations / access | Supabase CLI migrations + supabase-js | SQL migrations in the repo; typed client for queries |
| Auth | Supabase Auth with FACEIT OAuth (OIDC) | Proves account ownership; admin role enforced with row-level security |
| FACEIT data | FACEIT Data API from server code, cached in Postgres | Level and Elo lookup without hitting rate limits |
| Notifications | Telegram Bot API + email (Resend or SMTP) | Instant admin alerts, free |
| Deployment | Vercel (app) + Supabase (data) | Git-push deploys, automatic HTTPS, free tiers cover an MVP |
| Backups / CI | Supabase backups + GitHub Actions | Check what your Supabase plan includes; export with pg_dump if needed |

This matches the Supabase and Vercel suggestion in the proposal. Skip realtime: use 10–15 second polling on the availability calendar and the admin inbox. Before committing, confirm that Supabase can use FACEIT as a custom OAuth/OIDC provider; if not, handle the FACEIT OAuth flow in a Next.js route and create the session from there.

# 2. Scope for One Week

- Build: slot requests with a calendar, a 5v5 request board, tournament pages and registration with the FACEIT level check, manual admin check-in, Telegram and email alerts, and the admin panel.

- Cut: teams and invites (a team is just a name plus a captain at registration), Elo balancing, brackets, leaderboards, payments, memberships, analytics, and automated reminders.

# 3. SDLC Mapped to 7 Days

## Day 0 (today): Requirements and setup

- Create the FACEIT developer app (API key plus OAuth client) and the Telegram bot. Do this first, because approval can take time and everything else depends on it.

- Fix the business rules: cabins, opening hours, slot length, tournament level ranges, and who counts as admin.

- Fallback if OAuth is delayed: nickname lookup, with the admin verifying ownership manually.

## Day 1: Design

- Write the schema: users, cabins, slot_requests, match_requests, teams, tournaments, registrations, notifications_log.

- Add the exclusion constraint on (cabin_id, tstzrange(start, end)) for approved slots.

- Sketch the API endpoint list and 6–8 rough wireframes (booking, board, tournament, admin inbox).

- Create the Supabase project (use a separate dev project), the repo, and the Supabase CLI migration baseline.

## Day 2: Foundation

- FACEIT OAuth login, user profile with level and Elo cached, and role-based row-level security policies (player / admin).

- Base Next.js layout, mobile navigation, and Supabase client setup.

- Deploy a "hello world" to Vercel now, connected to Supabase, so deployment problems show up early.

## Day 3: Booking and notifications

- Availability calendar and slot request form with a status view (pending, approved, rejected).

- Telegram and email notifier called from server-side code that writes to notifications_log.

## Day 4: Matchmaking and tournaments

- 5v5 request board: join solo or as a team, plus a looking-for-players list.

- Tournament list and detail pages, registration with the level-range check, and entry limits.

## Day 5: Admin panel

- Single inbox for slots and registrations with approve and reject.

- Tournament create and edit, a player list with ban, and a check-in toggle.

- Verify that admin routes are enforced on the server, not just hidden in the UI.

## Day 6: Testing and hardening

- Automated tests (Vitest or Playwright) for the critical paths: double-booking rejection, level-range check, and admin-only access.

- Run a real concurrent-booking test.

- Manual mobile testing, rate limiting, CORS, input validation, and a FACEIT-API-down fallback that serves cached data.

## Day 7: Release and maintenance

- Production deploy on Vercel with the domain, a separate production Supabase project, and a backup plan (confirm what your Supabase plan includes) with a test restore.

- Seed the real cabins and a first tournament.

- Run a pilot with a few real players, then a 30-minute admin walkthrough.

- Set up uptime monitoring (UptimeRobot) and keep a bug list for week 2.

# 4. Risks to Watch

- FACEIT OAuth approval delay is the biggest schedule risk, hence Day 0.

- If you fall behind, drop the 5v5 board polish before touching booking or tournaments, since those are what the venue actually needs.

- Keep the first launch small: invite your regular players first.